## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Dark
Gantt Chart
Company name | Gogeta and Vegito |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Noor Alani
Project Start Date: | 2023-03-20 |  |  |  |  | March | [13 empty] | April | [27 empty] | May
Scrolling Increment: | 0 | time axis 2023-03-20 to 2023-05-14
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Iteration 1
Complete all sprint requirements | Goal | Name | 100% | 2023-03-20 | 18 | M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2
Write the Group Meeting Report | Low Risk |  | 100% | 2023-03-20 | 2
Create a stakeholder register | Low Risk |  | 100% | 2023-03-22 | 7
Design 3 personas | Med Risk |  | 100% | 2023-03-27 | 8
Write an evaluative report for the sprint | Med Risk |  | 100% | 2023-04-04 | 3
Product of Iteration 1 complete | Milestone |  | 100% | 2023-04-07 | 1 | bar: F
Iteration 2
Complete all sprint requirements | Goal |  | 100% | 2023-04-07 | 28 | F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2
Write the Group Meeting Report | Low Risk |  | 100% | 2023-04-07 | 7
Create a Resource List list | Med Risk |  | 100% | 2023-04-14 | 7
Create a Gantt Chart | Low Risk |  | 100% | 2023-04-21 | 7
Create a Github Repository | Low Risk |  | 100% | 2023-04-28 | 7
Write an evaluative report for the sprint | Med Risk |  | 100% | 2023-04-30 | 3
Product of Iteration 2 complete | Milestone |  | 100% | 2023-05-05 | 1 | bar: F
Iteration 3
Complete all sprint requirements | Goal |  | 100% | 2023-05-05 | 20 | F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2
Write the Group Meeting Report | Low Risk |  | 100% | 2023-05-05 | 4
Write a risk register | High Risk |  | 100% | 2023-05-09 | 4
Upload E-commerce website code | Med Risk |  | 100% | 2023-05-13 | 4
Carry out User Acceptance Tests | Low Risk |  | 100% | 2023-05-17 | 5
Write an evaluative report for the sprint | Med Risk |  | 100% | 2023-05-22 | 2
Product of Iteration 3 complete | Milestone |  | 100% | 2023-05-24 | 1
To add more data, Insert new rows ABOVE this one